## Project
Project Overview
PE Owners (If Applicable): | JMAN - PE
Client | JMAN - Client
Project Code: | JMCLI_001
Project Name: | <Project name>
Client Informations
Client Name | JMAN - Client
Business
Requirements
Features
Estimated Time | 1 week
Deliverables
Technical Approach | Requests , Playwright(Backup approach)
Scope
Additional Costs
Potential Blockers | Cloudflare, Rate Limit
Mitigation Plan | Utilzing the Playwright based approach
Achievements
Total websites | Easy to scrape | Moderate | Hard
5 | 3 | 0 | 2
Resourcing
For the Data extraction will be required below expertise
3 X Data Engineer | 100 FTE %
API cost & IP cost
| Cost | account count | Comment
Alternate Sources
dataplor (€0.08 / record) | Global Quick Service Restaurant Location Data ¦ 100K+ Businesses ¦ 250 Countries & Territories ¦ Supply Chain ¦ Site Selection ¦ Datarade
Plugindata (€0.10 / record) | Restaurant Database Worldwide: 4M+ Restaurants, bars and cafes from 240 Countries, Expansion Opportunities ¦ Datarade
Using serpAPI or google API to fetch restaurant data from Search Engines
Using serpAPI or google maps API or OpenStreetMaps API to fetch restaurant data from Map Apps

## Web Scraping Feasibility
Feasibility Analysis
Note: | This template helps with conducting feasibility checks and identifying blockers for web scraping projects on websites.
# | Site Name | URL | Credentials | Tech | Method | Run Time Test(1 hit) | Run Time Test(100 hits) | Has Blockers? | Blockers | Proxy Required? | VM Required? | Total of data(No) | Build Scrapper Time(hours) approx* | Language | Difficulty level | Estimate Days to extract all Data | Owner | Mitigation Plan | Comments
1 | Priem | https://www.priem.be | None | Python | Playwright | 0.7s | 90s | Y | Javascript based rendering website | N | N | Not Estimated | 1 hr | Dutch | Easy | Not Estimated | Srimathi |  | Javascript rendered webpage, 722 requests per 10 mins
2 | Aquilae | https://aquilae.be | None | Python | Request | 2.5s | 257s | Y | reCAPTCHA | N | N | Not Estimated | 6-10 hrs | Dutch | Hard | Not Estimated | Srimathi | Use Playwright for Further Scraping | 205 requests per 10 mins
3 | Hillewaere Insurance | https://www.declercq-verstichel.be | None | Python | Request | 3s | 297s | Y | Cookies pop up, reCAPTCHA,cloudfare | N | N | Not Estimated | 6-10 hrs | Dutch | Hard | Not Estimated | Srimathi | Use Playwright for Further Scraping | 196 requests per 10 mins
4 | Kris De Ridder - Insurance Broker | https://www.deridderkris.be | None | Python | Playwright | 1s | 67s | Y | Cookies pop up, Javascript based rendering website | N | N | Not Estimated | 1 hr | Dutch | Easy | Not Estimated | Srimathi |  | Javascript rendered webpage, 2019 requests per 10 mins
5 | Invicta Insurance | https://www.invicta-art.com | None | Python | Request | 1s | 57s | Y | reCAPTCHA | N | N | Not Estimated | 1 hr | French | Easy | Not Estimated | Srimathi | Use Playwright for Further Scraping | 222 requests per 10 mins

## Datapoints
Data Points
Note: | Identifying and collecting essential data points (fields) from websites
# | Websites | Datapoints
1 | Just Eat - Italy | Restaurants name
Restaurants Id
Restaurants unique name
Restaurants address
Restaurants rating
Restaurants timings
Restaurants cuisines
Restaurants availability
Restaurants ETA
2 | Deliveroo - italy | Restaurants name
Restaurants ETA
Restaurants rating
Restaurants min cost
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address
3 | Glovo - Italy | Restaurants name
Restaurants ETA
Restaurants rating
Restaurants offers
Restaurants Contact
Restaurants service cost
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address
4 | DoorDash - USA | Restaurants name
Restaurants ETA
Restaurants rating
Restaurants offers
Restaurants Contact
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address
5 | Uber Eats - USA | Restaurants name
Restaurants Id
Restaurants ETA
Restaurants Location
Restaurants timings
Restaurants description
Restaurants service cost
Restaurants menu
6 | GrubHub - USA | Restaurants name
Restaurants Id
Restaurants delivery fee
Restaurants min cost
Restaurants Contact
Restaurants offers
Restaurants ETA
Restaurants rating
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address

## Lookup (hidden)
IP Blocker | Easy
Captcha | Moderate
Press & Hold Button | Hard
Others